## OVERVIEW
The Priority defination:
priority | comments
0 | important and urgent
1 | urgent not important
2 | important not urgent
3 | not important and urgent
update history
NO. | Date | Modifier | comments
1 | 2014-12-30 | Jason Wang | add EN026-47

## Enhancement
ECN NO. | Title | Description | Type | Reporter | Create Time | Priority | Sub-priority | Developer | DEV Schedule/Work days | DEV status | DEV Comments | Reporter verify | comments | QA member | DEV commits | Schedule | DEV member | DEV status | Type
EN001 | behavior check tag option sensitive | tag options can be detected and supported by behavior check (conf use fixed path, while tag change the path) | App Tools | yibin sun | 2014-04-16 | 0 |  | Yu Zhao |  | Done | YES,shawn need to add –tag=** when call check function. | Done |  | ping chen | YES | WW18 | Shawn Yan | Done | Core Script
EN002 | BQS_script DSP QoR support | DSP QoR still use old trunk, need to be updated to BQS | Core Script | strdom fang | 2014-04-16 | 0 |  |  |  | Done |  | Done | Finish 20140903 | diansheng tao | NO | WW19 | Yu Zhao | On Track | App Tools
EN003 | BQS_script timeout control | Kill process when runtime too long | Core Script | jason wang | 2014-04-16 | 1 |  | Yu Zhao |  | Done | YES | Done | par timeout value should be 2 hours, no kill message output | cherry xu |  | WW20 | Both | Cancel | Report Style
EN004 | multi-window for multi-run | Multi-window for multi-run, for example, use 3 processor, then generate 4 windows. One for control and three for run.( do not create new window for each test case) | App Tools | yibin sun | 2014-04-16 | 1 |  | Yu Zhao |  | Done | YES | Done |  | robinson meng |  | WW21 |  | At Risk | Web Show
EN005 | Dynamic show process running | Dynamic show process running (for example, use “…” to let user know the flow is running) | Core Script | jason wang | 2014-04-16 | 2 |  | Yu Zhao |  | Done | YES | done |  | yuanyuan chen |  | WW22
EN006 | Output file have a meaningful name | generate file name format, and explanation | Core Script | jason wang | 2014-04-16 | 1 |  | Yu Zhao |  | Done | YES, we need to add temp_lock_file.log | done | nothing changed for BQS script output file name | rachel yan |  | WW23 |  |  | Others
EN007 | suite config file support | test suite script config file support | App Tools | yibin sun | 2014-04-16 | 1 |  | Yu Zhao |  | Done | YES | done |  | yibin sun |  | WW24
EN008 | report file format enhancement | Peter need to change to solid line, bold font in scan report. | Report Style | peter zhou | 2014-04-16 | 1 |  |  | 5/30 | Done |  | Done |  | jason wang |  | WW25
EN009 | define the report for web run | define the report for web run | Web Show | peter zhou | 2014-04-16 | 0 |  | Yu Zhao | 5/30 | Done | Will provide report without order | done |  | weixing tan |  | WW26
EN010 | Synthesis report scan problem (LSE) | Script not support synthesis report scan (memory, runtime) while synthesis tool is LSE | Core Script | strdom fang | 2014-04-22 | 0 |  | Yu Zhao |  | Done | YES | Done |  | bohong chen
EN011 | smart scan report | When scan report, please according to the case list and just scan the cases which in the case list. | App Tools | jeffrey ye | 2014-05-04 | 0 |  | Yu Zhao |  | Done | YES | Done |  | strdom fang
EN012 | BQS web access | Add BQS web access | Web Show | sean zhou | 2014-05-05 | 0 |  | Yu Zhao |  | Done | YES, Have been done for a long time | Done |  | jeffrey ye
EN013 | collect all APP tools in the same folder | Currently some of the application tools located in a deep directory, it is difficult for use and search. Please flat all application tools in the root directory (BQS_script/tools). | App Tools | jason wang | 2014-05-05 | 0 |  | Yu Zhao |  | Done | yes | Done |  | dwyane yang
EN014 | script breakpoint resume support | script should support skip running while the result is ok | App Tools | yibin sun | 2014-05-12 | 0 |  | Yu Zhao |  | Done |  | Done |  | sean zhou
EN015 | xml file auto update | Update xml file automatically without manually add a bat command | App Tools | yibin sun | 2014-05-12 | 0 |  | Yu Zhao |  | Cancel |  | Advise user to move this usage into export script time | document know user update xml file | fengying wang
EN016 | BQS script add option to disable impl flow | we need add one more option to disable the implementation flow | Core Script | jason wang | 2014-05-15 | 0 |  | Shawn Yan |  | Cancel | new default behavior defined, unnecessary for this option. |  |  | douglas lv
EN017 | CMD flow use default value to generate files | in CMD flow, we should use default values for project and impl while there is not values given to generate the output file name. | Core Script | jason wang | 2014-05-22 | 0 |  | Shawn Yan |  | Done |  | Done |  | xiaoliang zhang
EN018 | behavior check support non-default job location | when BQS script use different value of job-dir or tag then the default value, the behavior will failed to check the flow result. | Core Script | yibin sun | 2014-05-28 | 0 |  | Yu Zhao |  | Done |  | Done |  | sally sun
EN019 | CMD flow default workdir | in CMD flow, if the config file user must add "./" for the file path, if user lost this current path, script cannot find the file | Core Script | peter zhou | 2014-07-02 | 0 |  | Yu Zhao |  | Done |  |  |  | zhilong su
EN020 | use EXCEL file as config | run behavior check with the Excel file(a suite lookup table) | App Tools | peter zhou | 2014-06-25 | 1 |  | Yu Zhao |  | Done |  |  |  | jeffrey chen
EN021 | standard alone config file | collect all test suite confige in a stand alone folder(use lookup table to get this config file) | App Tools | peter zhou | 2014-06-25 | 1 |  | Yu Zhao |  | Done |  |  |  | peter zhou
EN022 | report add diamond version add time | add Diamond version and run time in the test report | Report Style | ping chen | 2014-07-17 | 0 |  | Yu Zhao |  | Done | only time added | Done |  | shawn yan
EN023 | Rerun failed case(license) | if case failed with license problem or oher issue rerun it | Core Script | jason wang | 2014-09-04 | 0 |  | Shawn Yan |  | Done |  | Done |  | yu zhao
EN024 | Rerun easily | script generate error case command line for user rerun | App Tools | jason wang | 2014-09-04 | 0 |  | Yu Zhao |  | Done |  | Done
EN025 | Kill message record | record kill message to the case directory | App Tools | jason wang | 2014-09-04 | 0 |  | Yu Zhao |  | Done |  | Done
EN026 | pre/post case entry | script should support pre/post user script | Core Script | jason wang | 2014-09-28 | 2 | 2.1 | Shawn Yan | 4
EN027 | Multi-check support | BQS standard case need to support check different parts according different check options | Core Script | jason wang | 2014-11-13 | 2 | 2.1 | Yu Zhao | 2 |  |  |  | see sheet multi-check for details
EN028 | NCL dump support | script should support ncd2ncl dump for both map and par, this will help the regression case build | Core Script | jason wang | 2014-11-26 | 1 | 1.2 | Shawn Yan | 3
EN029 | QoR run case record | script should show test suite case number and real calculate case number for general QoR, LSE QoR(zhilong), web compare page, web QoR page. | App Tools | yibin sun | 2014-12-04 | 0 |  | Yu Zhao |  | Done |  |  | see QoR_num for detail show
EN030 | Simulation compile option support | while user have a .do file please just replace the path not the whole line and regenerate it(this will lost some extra options for compile command | Core Script | strdom fang | 2014-12-04 | 0 | 0.1 | Shawn Yan | 3
EN031 | IP regression | support IP regression on bqs web platform | Others | sally sun | 2014-12-01 | 1 | 1.1 | Yu Zhao | 2
EN032 | LSE ENCRYPT support | LSE encrypt Support on bqs web platform | Others | peter zhou | 2014-12-30 | 2 | 2.3 | Yu Zhao | 2
EN033 | BQS case list next step | define and DEV the next case list format for BQS use | Core Script | yibin sun | 2014-12-30 | 1 | 1.2 | Yu Zhao | 10
EN034 | BQS fail case rerun | user can rerun all failed case with one button on the bqs webpage | Web Show | peter zhou | 2014-12-30 | 2 | 2.2 | Yu Zhao | 1
EN035 | BQS web usage | create BQS webpage usage documents | Web Show | jason wang | 2014-12-30 | 3 | 3.1 | Yu Zhao | 3
EN036 | BQS new Client schedule | meeting with lsv to schedule for the new BQS client | Web Show | yu zhao | 2014-12-30 |  |  | Yu Zhao | NA
EN037 | BQS QoR best seed report | BQS web support QoR best SEED sort and report | Web Show | yibin sun | 2014-12-30 | 1 | 1.5 | Yu Zhao | 2
EN038 | BQS client add kill useless process | BQS client add kill time out(default 5 hours) diamond process | Core Script | sally sun | 2014-12-30 | 0 | 0.1 | Yu Zhao | 1
EN039 | BQS multi check support | BQS support multi check based on the user input | Core Script | yibin sun | 2014-12-30 | 2 |  | Yu Zhao |  | Cancel
EN040 | BQS support classical flow | BQS support Classical flow(impl, simulation, check, report) | Core Script | jason wang | 2014-12-30 | 0 | 0.2 | Both | 2
EN041 | LSE daily support on bqs web | LSE daily support on bqs web | Others | zhilong su | 2014-12-30 | 2 | 2.4 | Yu Zhao | NA
EN042 | Client priority support | make the machine owner have a higher priority on his/her test suite run on this machine | Core Script | yibin sun | 2014-12-30 | 1 | 1.3 | Both | 3
EN043 | smart cross suite support | increase the CPU utilization with current suite file flow | Core Script | zhilong su | 2014-12-30 | 2 | 2.5 | Yu Zhao | 2
EN044 | Squish flow on linux | bqs platform support squish flow on linux platform | Core Script | rachel yan | 2014-12-30 | 1 | 1.1 | Shawn Yan | 5
EN045 | BQS email support | BQS support email function when job finished | Core Script | jason wang | 2014-12-30 | 2 | 2.2 | Shawn Yan | 2
EN046 | LST file compare and update | LST file compare and replace if specified by owner | Others | peter zhou | 2014-12-30 | 2 | 2.3 | Shawn Yan | 5
EN047 | BQS version release | release our BQS with new feature documents | Others | jason wang | 2014-12-30 | 1 | 1.4 | Shawn Yan | NA

## multi_check
BE test case need to be reused for different test, for example one test case need to be used for STA, SIM, IBIS.
So for this one test case different people need to run and check those sections they wanted.
test case show:
models
others
par
sim
source
bqs.info
| sta.conf | >> | content in this file:
[configuration information]
area = conn
type = conn
[method]
check_line_1 = 1
check_flow = 1
[check_line_1]
title = sta_check
check_line = clock frequency 10MHz
[check_flow]
file=./_scratch/Impl1/prj_top_Impl1.par
| ibis.conf | >> | content in this file:
[configuration information]
area = conn
type = conn
[method]
check_line_1 = 1
check_flow = 1
[check_line_1]
title = ibis_check
check_line = ibis xxxxxx
[check_flow]
file=./_scratch/Impl1/prj_top_Impl1.par
| sim.conf | >> | content in this file:
[configuration information]
area = conn
type = conn
[method]
check_block_1 =1
check_flow = 1
[check_block_1]
title = rtl_par
golden_file = ./_scratch/sim_rtl/test_vector.out
compare_file = ./_scratch/sim_par_vlg/test_vector.out
[check_flow]
file=./_scratch/Impl1/prj_top_Impl1.par
command line entry:
add option --check-entry=sta, sim, ibis for check different conf file

## QoR_num
Priority0 | sapphire
|  |  | E60_sapphire_lse | L25_sapphire_lse | Average | Variation |  |  | fmax | Register | LUT | Slice | ParPeakMem | Total_cpu_time
calculated/total |  | fmax | 1.445% | -0.001% | 1.032% | 127.9% | pass | <-15% | 3 | 5 | 7 | 7 | 3 | 3
<20>/<92> |  | Register | -3.265% | -2.865% | -3.151% | 96.7% | pass | -15%~-5% | 13 | 5 | 8 | 5 | 2 | 1
|  | LUT | -3.024% | -3.844% | -3.258% | 125.9% | pass | -5%~5% | 58 | 80 | 71 | 75 | 25 | 13
|  | Slice | -2.935% | -3.052% | -2.968% | 115.4% | pass | 5%~15% | 10 | 2 | 5 | 2 | 2 | 6
|  | ParPeakMem | - | -1.383% | -1.383% | 25.37% | pass | >15% | 8 | 0 | 1 | 3 | 0 | 9
|  | Total_cpu_time | - | 17.04% | 17.04% | 226.8% | pass
NEW REQUIREMENT